| Иформация о предлагаемых для софинансирования гуманитарных проектах |  |
| --- | --- |
| 1.Наименование проекта: Мир без ограничений |  |
| 2. Срок реализации проекта: 12 месяцев с начала реализации проекта |  |
| 3. Организация – заявитель, предлагающая проект: Государственное учреждение «Территориальный центр социального обслуживания населения Ушачского района» |  |
| 4. Цели проекта: Реабилитация детей-инвалидов, молодых инвалидов, людей с инвалидностью путем использования современных технологий и методов сенсорной интеграции для восстановления и приобретения жизненно-важных навыков и способностей для полноценной жизни |  |
| 5. Задачи, планируемые к выполнению в рамках реализации проекта: 1. Создание и оборудование сенсорной комнаты. 2.Обучение специалистов для работы на сенсорном оборудовании. 3.Обеспечение информационного сопровождения проекта. |  |
| 6. Целевая группа: 1. Молодые инвалиды, люди с инвалидностью, страдающие депрессиями, стрессами, нарушениями функционирования органов чувств (зрения, слуха, речи), функций опорно-двигательного аппарата, страдающие соматическими болезнями, сопровождающимися повышенным уровнем тревожности. 2. Дети-инвалиды, страдающие неврозами, задержкой речевого развития, заиканием, вследствие поражения центральной нервной системы, всеми формами детского церебрального паралича, нарушениями слуха, зрения и речи. |  |
| 7. Краткое описание мероприятий в рамках проекта: В рамках реализации задачи № 1 планируется: 1.1. Ремонт помещения для оборудования сенсорной комнаты. 1.2.Проведение тендера по закупкеи установке оборудования. 1.3. Закупка и установка оборудования. 1.4. Оформление релаксационного и активационного блока сенсорной комнаты. В рамках реализации задачи № 2 планируется: 1.1. Изучение программ по самообразованию для работы в сенсорной комнате специалистами и психологом. 1.2. Популяризация волонтерства среди молодежи, в особенности с медицинским образованием. 1.3. Проведение мастер-класса «Сенсорная комната - комната-лекарь». В рамках реализации задачи № 3 планируется: 1.Беседы с родителями по проблемам развития детей-инвалидов. 2. Анкетирование родителей, воспитывающих детей-инвалидов. 3. Проведение мастер-класса для родителей «Игры – релаксация для детей и взрослых». 4.Проведение «Дня открытых дверей». 5. Изготовление мини-банеров «Мир без ограничений». 6. Подготовка и представление материалов по тематике проекта в районную газету «Патриот», на официальный сайтУшачского районного исполнительного комитета ushachi.vitebsk-region.gov.by |  |
| 8. Общий объем финансирования (в долларах США): 13232 |  |
| Источник финансирования | Объем финансирования (в долларах США) |
| Средства донора | 13000 |
| Софинансирование | 232 |
| 9. Место реализации проекта (область/район, город): Отделение социальной реабилитации, абилитации инвалидов при государственном учреждении «Территориальный центр социального обслуживания населения Ушачского района» расположено по адресу: Витебская область, Ушачский район, д. Граденец, ул. Центральная, д. 3 Б |  |
| 10. Контактное лицо: инициалы, фамилия, должность, телефон, адрес электронной почты Измайлович Ольга Александровна – директор ГУ «Территориальный центр социального обслуживания населения Ушачского района» + 375 (2158) 52847, e-mail: ushachi.r-tc@mintrud.by |  |

| Information on the Humanitarian Projects to Be Co-Financed |  |
| --- | --- |
| 1. Project name: A World without Limitations |  |
| 2 Project implementation period 12 months from the implementation date |  |
| 3. Applicant organization that proposes a project: State institution "Ushachi Local Social Care Center " |  |
| 4. Project Goals: Rehabilitation of disabled children, young people and adults with disabilities through the use of modern technologies and methods of sensory integration to restore and acquire vital skills and abilities necessary for full life |  |
| 5. Tasks to be fulfilled in the framework of the project: 5.1. Creation and equipment provision for the sensory room 5.2. Training of specialists who’ll work on the sensory equipment 5.3. Project information support |  |
| 6. Target Group: 6.1. Disabled young people, people with disabilities, suffering from depression, stress, disruption of the sense organs functioning (vision, hearing, speech), disruption of the musculoskeletal system functions, those suffering from somatic disorders accompanied by an increased level of anxiety. 6.2. Disabled children suffering from neurosis, delayed speech development, stuttering, due to damage to the central nervous system, all forms of cerebral palsy, hearing, vision and speech impairments. |  |
| 7. Brief description of the project activities: Activities to fulfill task 1: 7.1.1. Restoration/renovation of premises for the sensory room. 7.1.2. Tendering for the purchase and installation of equipment. 7.1.3. Purchase and installation of equipment. 7.1.4. The design of the relaxation and activation unit of the sensory room. Activities to fulfill task 2: 7.2.1. The study of self-education programs on working in the sensory room by the specialists and the psychologist. 7.2.2. Popularization of volunteering among young people, especially those with medical education. 7.2.3. Master-class "A Sensory Room is a Room-healer." Activities to fulfill task 3: 7.3.1. Talks with parents about difficulties in development of children with disabilities. 7.3.2. Questioning of parents raising disabled children. 7.3.3. A master class for parents "Games are a means of relaxation for children and adults." 7.3.4. "Doors Open Day”. 7.3.5. Production of mini-banners "World without Limitations ". 7.3.6. Preparation and submission of materials on the subject of the project to the district newspaper “Patriot”, on the official website of the Ushachi District Executive Committee. |  |
| 8. Total Funding (in USD): 13,232 |  |
| Source of funding | Amount of funding (in US dollars) |
| Donor funds | 13,000 |
| Co-financing | 232 |
| 9. Location of the project (region / district, city): The Day care department for disabled people at the state institution "Ushachi Local Social Care Center" is located at the following address: 3 Б Sentralnaya street, Gradenets Village, Ushachy District, Vitebsk Region. |  |
| 10. Contact person: initials, last name, position, phone number, email address Izmailovich Olga Alexandrovna- Director of the State Institution "Ushachi Local Social Care Center " tel.+ 375 (2158) 52847 e-mail: ushachi.r-tc@mintrud.by |  |